## Sheet1
Risk ID | Description | Likelihood | Impact | Score | Current Controls | Recommended Controls | Owner | Status
R1 | Legal RF Interference | 2 | 5 | 10 | Supervisor approval, no live jamming | Use emulation only, remove RF-TX libs, shielded tests if needed | Supervisor | Open
R2 | Flight / Physical Safety | 3 | 5 | 15 | Controlled indoor tests, protective cage | Pre-flight checklist, PPE, staged testing | Lab Safety Officer | Open
R3 | Technical Integration Failure | 3 | 4 | 12 | Basic bench tests done | Add watchdog, incremental integration, auto-land failsafe | Research Team | Open
R4 | AI Misclassification | 3 | 4 | 12 | Initial dataset prepared | Cross-validation, diverse data, human-in-loop verification | Research Team | Open
R5 | Project Approval | 3 | 3 | 9 | Dean approval received | Maintain approval log, pre-book labs, fallback to simulation | Project Lead | Open
R6 | Limited Knowledge/Resources on Jamming | 3 | 3 | 9 | Literature review started | Faculty consultations, simulation focus, document assumptions | Research Team | Open
R7 | Reputational / Misuse Risk | 2 | 4 | 8 | Restricted repo sharing | Add disclaimer, redact sensitive modules, controlled release | Project Lead | Open
R8 | Battery / Power Constraint | 3 | 3 | 9 | Battery limits known | Spare batteries, short repeatable runs, log telemetry | Research Team | Open
R9 | Adversarial Spoofing vs Model | 2 | 3 | 6 | None | Add adversarial cases to test set, document limits | Research Team | Open
R10 | Hardware Failure / Supply Risk | 2 | 3 | 6 | Single unit available | Keep basic spares, order early, design tolerant tests | Project Lead | Open